## Engineer's Estimate
PRELIMINARY ENGINEER'S ESTIMATE
| WEST PINE STREET IMPROVEMENTS |  |  | AGENCY
City of Central Point
KIND OF WORK |  | LENGTH | DATE | ESTIMATOR
STREET IMPROVEMENTS |  | ~2300' | 2016-12-07 | KAL
ITEM # | ITEM DESCRIPTION | UNIT | AMOUNT | UNIT COST | TOTAL
00200 - TEMPORARY FEATURES AND APPURTENANCES
10 | MOBILIZATION | LS | 10% | 345000 | 345000 | 10% | 344923
20 | TEMPORARY PROTECTION AND DIRECTION OF TRAFFIC, COMPLETE | LS | 5% | 172500 | 172500 | 5.001%
30 | EROSION CONTROL | LS | 1% | 34500 | 34500 | 1%
00300 - ROADWORK
40 | CONSTRUCTION SURVEY WORK | LS | 2% | 69000 | 69000 | 2%
50 | REMOVAL OF STRUCTURES AND OBSTRUCTIONS | LS | 1 | 10000 | 10000
60 | REMOVAL OF SURFACINGS | SQYD | 11200 | 10 | 112000
70 | CLEARING AND GRUBBING | LS | 1 | 5000 | 5000
80 | GENERAL EXCAVATION | CUYD | 7700 | 17 | 130900
90 | SUBGRADE GEOTEXTILE | SQYD | 14000 | 1.5 | 21000
00400 - DRAINAGE AND SEWERS
100 | 6 INCH STORM SEWER PIPE, PVC, 5 FT DEPTH | FOOT | 540 | 45 | 24300
110 | 24 INCH STORM SEWER PIPE, PVC, 5 FT DEPTH | FOOT | 2100 | 60 | 126000
120 | CONCRETE STORM SEWER MANHOLES | EACH | 7 | 5000 | 35000
130 | CONCRETE INLETS, TYPE 4A | EACH | 20 | 1500 | 30000
140 | MINOR ADJUSTMENT OF MANHOLES | EACH | 10 | 1000 | 10000
00500 - BRIDGES
150 | REINFORCED CONCRETE BOX CULVERTS | FOOT | 200 | 1750 | 350000
160 | WINGWALLS AND APRONS | LS | 2 | 100000 | 200000
170 | PED BRIDGE | LS | 1 | 350000 | 350000
00600 - BASES
180 | AGGREGATE SUBBASE (3/4"-0") | TON | 5600 | 25 | 140000
190 | AGGREGATE BASE (4"-0") | TON | 8100 | 20 | 162000
00700 - WEARING SURFACES
200 | LEVEL 3, 1/2-INCH DENSE ACP MIXTURE | TON | 2800 | 100 | 280000
210 | CONCRETE CURBS, STANDARD CURB AND GUTTER | FOOT | 4350 | 15 | 65250
220 | CONCRETE WALKS | SQFT | 22500 | 5.5 | 123750
230 | CONCRETE DRIVEWAYS | SQFT | 9600 | 6.5 | 62400
00800 - PERMANENT TRAFFIC SAFETY AND GUIDANCE DEVICES
240 | THERMOPLASTIC, PROFILE, 90 MIL EXTRUDED | LF | 9000 | 2 | 18000
250 | PAVEMENT LEGEND, TYPE D: ARROWS | EACH | 8 | 260 | 2080
260 | PAVEMENT LEGEND, TYPE D: BICYCLE LANE STENCIL | EACH | 7 | 150 | 1050
270 | PAVEMENT BAR, TYPE D | SQFT | 100 | 20 | 2000
00900 - PERMANENT TRAFFIC CONTROL AND ILLUMINATION SYSTEMS
280 | REMOVE AND REINSTALL EXISTING SIGNS | LS | 1 | 5000 | 5000
290 | PERMANENT SIGNS | LS | 1 | 15000 | 15000
300 | STREET LIGHTS SINGLE - INCLUDING CONNECTIONS, WIRING AND CONDUIT | EACH | 38 | 9000 | 342000
01000 - RIGHT OF WAY DEVELOPMENT AND CONTROL
310 | LANDSCAPING | LS | 1 | 150000 | 150000
320 | IRRIGATION | LS | 1 | 50000 | 50000
330 | SINGLE MAILBOX SUPPORTS | EACH | 10 | 250 | 2500
340 | MULTIPLE MAILBOX SUPPORTS | EACH | 10 | 300 | 3000
| CONSTRUCTION SUBTOTAL |  |  |  | 3449230
| Consultant Preliminary Engineering |  |  | 15% | 517384.5
| Consultant Construction Engineering |  |  | 10% | 344923
| Contingencies |  |  | 5% | 172461.5
BID SUBTOTAL |  |  |  |  | 4483999
| ODOT Admin | LS | 1 | 15000 | 15000
| Right of Way Estimate |  |  |  | 50000
| TOTAL |  |  |  | 4548999

## Funding Breakdown Spreadsheet
| STBG | CMAQ | Local Funds | Other | Total
Project Development | 0
Design/Engineer | 0 | 517385 | 344923 |  | 862308
Right of Way | 0 |  | 50000 |  | 50000
Construction | 1000000 | 1000000 | 1449230 |  | 3449230
Other | 187462 |  | 0 |  | 187462
0
Total | 1187462 | 1517385 | 1844153 |  | 4549000
City Match SD Fund |  | 775000
City Match SD WQ Fund |  | 350000
Jackson County |  | 45000
City Street Fund |  | 450000
City Street SDCS |  | 250000
1870000
2678999