## English Scoping Sheet
RVMPO/MRMPO SCOPING ESTIMATE
(updated June 2016)
PROJECT NAME | OR 140: EXIT 35 BLACKWELL ROAD |  |  | COUNTY | Jackson
KIND OF WORK | GENERAL CONSTRUCTION | LENGTH | DATE | ESTIMATE PREPARER
|  | 1.13 M | 2016-11-16 | Roy Blower
BID ITEM # | ITEM TITLE | UNIT | QTY | UNIT | EXTENDED
|  |  |  | COST | COST
TEMPORARY FEATURES AND APPURTENANCES
0210-0100000A | MOBILIZATION | LS | x | 10% | 40431.976
0225-0100000A | TEMPORARY PROTECTION AND DIRECTION OF TRAFFIC | LS | x | 8% | 32345.5808
0280-0100000A | EROSION CONTROL | LS | x | 2% | 8086.3952
ROADWORK
0305-0100000A | CONSTRUCTION SURVEY WORK | LS | x | 1% | 3887.69
0310-0100000A | REMOVAL OF STRUCTURES AND OBSTRUCTIONS | LS | x | 3% | 11663.07
0310-0101000F | REMOVAL OF CURBS | FOOT |  | 3 | 0
0310-0113000A | REMOVAL OF GUARDRAIL | FOOT |  | 3 | 0
0310-0100000F | REMOVAL OF PIPES | FOOT |  | 16 | 0
0310-0103000J | REMOVAL OF SURFACINGS | SQYD |  | 5 | 0
0310-0102000J | REMOVAL OF WALKS AND DRIVEWAYS | SQYD |  | 8 | 0
0320-0100000R | CLEARING AND GRUBBING | ACRE | 0.5 | 5000 | 2500
0330-0105000K | GENERAL EXCAVATION | CUYD | 5000 | 17 | 85000
0330-0123000K | EMBANKMENT IN PLACE | CUYD | 2500 | 0 | 0
0331-0106000J | 18 INCH SUBGRADE STABILIZATION | SQYD | 1000 | 15 | 15000
0331-0112000J | 24 INCH SUBGRADE STABILIZATION | SQYD |  | 20 | 0
0340-0100000Q | WATERING | MGAL |  | 25 | 0
0350-0105000J | SUBGRADE GEOTEXTILE | SQYD | 15500 | 1 | 15500
0390-0105000K | LOOSE RIPRAP, CLASS 50 | CUYD |  | 56 | 0
0390-0108000K | LOOSE RIPRAP, CLASS 100 | CUYD |  | 60 | 0
DRAINAGE AND SEWERS
0445-010018AF | 18 INCH CULVERT PIPE, 5 FT DEPTH | FOOT |  | 68 | 0
0445-010024AF | 24 INCH CULV PIPE, 5 FT DEPTH | FOOT |  | 75 | 0
0445-010036AF | 36 INCH CULV PIPE, 5 FT DEPTH | FOOT |  | 101 | 0
0445-010048AF | 48 INCH CULV PIPE, 5 FT DEPTH | FOOT |  | 142 | 0
0445-035012AF | 12 INCH STORM SEWER PIPE, 5 FT DEPTH | FOOT |  | 49 | 0
0445-035015AF | 15 INCH STORM SEW PIPE, 5 FT | FOOT |  | 56 | 0
0445-035018AF | 18 INCH STORM SEWER PIPE, 5 FT DEPTH | FOOT |  | 65 | 0
0445-035024BF | 24 INCH STORM SEWER PIPE, 10 FT DEPTH | FOOT |  | 95 | 0
0445-035036BF | 36 INCH STORM SEWER PIPE, 10 FT DEPTH | FOOT |  | 119 | 0
0445-035048BF | 48 INCH STORM SEWER PIPE, 10 FT DEPTH | FOOT |  | 220 | 0
0470-0101000E | CONCRETE STORM SEWER MANHOLES | EACH |  | 3550 | 0
0470-0307000E | CONCRETE INLETS, TYPE CG-2 | EACH |  | 1500 | 0
0480-0100000F | DRAINAGE CURBS | FOOT |  | 10 | 0
0490-0100000E | ADJUSTING BOXES | EACH |  | 290 | 0
0490-0105000E | ADJUSTING INLETS | EACH |  | 715 | 0
0490-0121000E | MAJOR ADJUSTMENT OF MANHOLES | EACH |  | 1500 | 0
BRIDGES/STRUCTURES
| Box Culvert (26ft extention) | LS | 1 | 30550 | 30550
| TEMP BRIDGE | LS |  |  | 0
| BRIDGE REMOVAL | LS |  |  | 0
| RETAINING WALL | LIN FT |  | 492 | 0
BASES
0620-0104000J | COLD PLANE PAVEMENT REMOVAL, 0 - 2 INCH DEEP | SQYD |  | 3 | 0
0620-0120000J | COLD PLANE PAVEMENT REMOVAL, 2 INCH DEEP | SQYD |  | 1 | 0
0640-0100000M | AGGREGATE BASE | TON | 5500 | 15.15 | 83325
0640-0101000M | AGGREGATE SHOULDERS | TON |  | 20 | 0
WEARING SURFACES
0730-0100000M | ASPHALT IN TACK COAT | TON | 2 | 575 | 1150
0744-0202000M | LEVEL 2, 1/2 INCH DENSE MHMAC | TON | 1500 | 76 | 114000
0744-0302000M | LEVEL 3, 1/2 INCH DENSE MHMAC | TON |  | 90 | 0
0746-0100000F | PG 64-22 ASPHALT OIL | TON | 80 | 450 | 36000
0749-0100000E | EXTRA FOR ASPHALT APPROACHES | EACH |  | 575 | 0
0755-0100000J | REINFORCED CONCRETE PAVEMENT | SQYD |  | 125 | 0
0759-0127000J | REINFORCED CONCRETE DRIVEWAYS | SQFT |  | 9 | 0
0759-0100000F | CONCRETE CURBS | FOOT |  | 17 | 0
0759-0103000F | CURB AND GUTTER CONCRETE CURBS | FOOT |  | 19 | 0
0759-0128000J | CONCRETE WALKS | SQFT |  | 5 | 0
0759-0126000J | CONCRETE DRIVEWAYS | SQFT |  | 7 | 0
PERMANENT TRAFFIC CONTROL AND GUIDANCE DEVICES
0810-0104000F | GUARDRAIL, TYPE 2A | FOOT | 187.5 | 16 | 3000
0810-0107000F | GUARDRAIL, TYPE 3 | FOOT |  | 50 | 0
0810-0109000F | GUARDRAIL, TYPE 4 | FOOT |  | 50 | 0
0810-0119000E | GUARDRAIL ANCHORS, TYPE 1 | EACH |  | 780 | 0
0810-0122000E | GUARDRAIL END PIECES, TYPE B | EACH |  | 700 | 0
0810-0126000E | GUARDRAIL TRANSITION | EACH |  | 2300 | 0
0810-0129000E | GUARDRAIL TERMINALS, NON-FLARED | EACH |  | 2150 | 0
0810-0130000E | GUARDRAIL TERMINALS, FLARED | EACH |  | 2100 | 0
0812-0101000F | ADJUSTING GUARDRAIL | FOOT |  | 3.5 | 0
0820-0100000F | CONCRETE BARRIER | FOOT |  | 61 | 0
0820-0127000F | CONCRETE BARRIER, TALL | FOOT |  | 85 | 0
0840-0102000E | DELINEATORS, TYPE 2 | EACH |  | 38 | 0
0840-0106000E | MILEPOST MARKER POSTS | EACH |  | 100 | 0
0867-0103000E | PAVEMENT LEGEND, TYPE B: ARROWS | EACH |  | 270 | 0
0867-0111000E | PAVEMENT LEGEND, TYPE B: "SCHOOL" | EACH |  | 495 | 0
0867-0119000E | PAVEMENT LEGEND, TYPE B: RAILROAD CROSSING MARKINGS | EACH |  | 975 | 0
0867-0131000E | PAVEMENT LEGEND, TYPE B-HS: BICYCLE LANE SYMBOLS | EACH |  | 280 | 0
0867-0145000J | PAVEMENT BAR, TYPE B | SQFT |  | 8.5 | 0
0867-0173000E | PAVEMENT LEGEND, TYPE B: DISABLED PARKING | EACH |  | 287 | 0
0855-0102000E | BI-DIRECTIONAL YELLOW TYPE I MARKERS | EACH |  | 4.75 | 0
0855-0103000E | BI-DIRECTIONAL YELLOW TYPE I MARKERS, RECESSED | EACH |  | 6 | 0
0860-0200000F | LONGITUDINAL PAVEMENT MARKINGS - PAINT | FOOT |  | 0.15 | 0
0865-0116600F | THERMOPLASTIC, EXTRUDED, SURFACE, PROFILED | FOOT |  | 1 | 0
0857-0101000L | CONTINUOUS RUMBLE STRIPS | MILE |  | 900 | 0
PERMANENT TRAFFIC CONTROL AND ILLUMINATION SYSTEMS
| PERMANENT SIGNS | LS |  |  | 0
| INTERPRETIVE PANELS AND DÉCORATIVE HARDSCAPE FEATURES | LS |  |  | 0
0990-0103000A | DETECTOR INSTALLATION, _____ | EACH |  | 2600 | 0
0990-0101000A | TRAFFIC SIGNAL INSTALLATION, _____ | EACH |  | 178000 | 0
0990-0105000A | INTERCONNECT SYSTEM | LS |  | 30000 | 0
| STREET LIGHTS SINGLE - INCLUDING CONECTIONS, WIRING, CONDUIT | EACH |  |  | 0
| STREET LIGHTS MULTIPLE - INCLUDING CONECTIONS, WIRING, CONDUIT | EACH |  |  | 0
| ILLUMINATION |  |  |  | 0
RIGHT-OF-WAY DEVELOPMENT AND CONTROL
1030-0109000R | PERMANENT SEEDING, MIX NO. 1 | ACRE | 1 | 2744 | 2744
1050-0135000F | _____ CHAIN LINK FENCE | LIN FT |  | 18 | 0
1070-0100000E | SINGLE MAILBOX SUPPORTS | EACH |  | 150 | 0
1070-0101000E | MULTIPLE MAILBOX SUPPORTS | EACH |  | 350 | 0
| ENVIRONMENTAL MITIGATION SITES | LS |  |  | 0
| LANDSCAPING | LS |  |  | 0
UNUSUAL ELEMENTS
1095-0104000E | LITTER RECEPTACLES | EACH |  | 1600 | 0
1095-0100000E | BENCHES, TYPE ________ | EACH |  | 1700 | 0
1040-0200000E | TREE GRATES | EACH |  | 1300 | 0
1095-0101000E | BIKE RACKS | EACH |  | 600 | 0
0759-0161000F | METAL HANDRAIL, 2 RAILS | LIN FT |  | 72 | 0
0
CONSTRUCTION SUBTOTAL |  |  |  |  | 485183.712
PROJECT PHASES/SUMMARY OF COSTS
ROW
| LAND, IMPROVEMENTS, DAMAGES | LS
| ROW PROCESS (APPR, REV APPR, ACQ, ODOT REV, etc.) | File |  | 10000 | 0 | 13 files for the path but highway project would be purchasing RoW for the path
| ROW SUBTOTAL |  |  |  | 0
UTILITY RELOCATION
INSERT APPROPRIATE LINE ITEMS/COSTS FOR ANY REIMBURSABLE UTILITIES
| UTILITY RELOCATION SUBTOTAL |  |  |  | 0
PRELIMINARY ENGINEERING
| PE - ODOT OVERSIGHT | LS | 1 | 20000 | 20000
| *PE - ENVIRONMENTAL | LS | 1 |  | 0
| PE - SURVEYING | LS | 1 |  | 0
| PE - GEO-TECH | LS | 1 |  | 0
| **PE - DESIGN & PROJECT MANAGEMENT | LS | 20% | of CON cost | 97036.7424
| PRELIMINARY ENGINEERING SUBTOTAL |  |  |  | 117036.7424
CONSTRUCTION
| TOTAL BID ITEM COST (from estimate above) |  |  |  | 485183.712
| CE- ODOT OVERSIGHT | LS | 1 | 20000 | 20000
| ***CONSTRUCTION ENGINEERING ADMIN & INSPECTION | LS | 20% | of CON cost | 97036.7424
| CONSTRUCTION CONTINGENCY | LS | 30% | of CON cost | 145555.1136
| CONSTRUCTION SUBTOTAL |  |  |  | 747775.568
TOTAL PROJECT COST |  |  |  |  | 864812.3104
* | Environmental costs should account for the typical clearances needed for each environmental area (historic-archaeological & built, hazmat, biology, wetland, noise, etc.), any necessary permits and land use requirements. Contact ODOT LAL for assistance, if needed.
** | Typical percentages for federally funded LPA projects range from 15% to 25%. Projects with lower construction costs (under $1M) typically have higher design percentages.
*** | Typical percentages for federally funded LPA projects range from 17% to 25%. Projects with lower construction costs (under $1M) typically have higher CE percentages.

## Budgeting Sheet
Project Name
| Year | Federal Funds Requested |  | Local Funds | Other | Total
|  | STBG | CMAQ
Proj. Devel.
Design/Engineer | 2019 |  | 104984.1 | 12015.9 |  | 117000
Right-of-Way
Construction | 2019 |  | 671180.4 | 76819.6 |  | 748000
Other
Total |  |  | 776164 | 88835.5 |  | 865000