## Cost Estimate Scoping Sheet
RVMPO/MRMPO SCOPING ESTIMATE
(updated March 2022)
PROJECT NAME | Delta Waters Rd - Nome Ct to Colonial Ave |  |  | COUNTY | Jackson
KIND OF WORK | Street Improvements, Sidewalk, and Striping | LENGTH | DATE | ESTIMATE PREPARER
|  | 3150' | 2025-05-26 | Karl MacNair, PE
Section # | ITEM TITLE | UNIT | QTY | UNIT | EXTENDED
|  |  |  | COST | COST
TEMPORARY FEATURES AND APPURTENANCES
210 | MOBILIZATION | LS | x | 10% | 930495.7878
221 | TEMPORARY PROTECTION AND DIRECTION OF TRAFFIC | LS | x | 10% | 930495.7878
280 | EROSION CONTROL | LS | x | 2% | 186099.1576
ROADWORK
305 | CONSTRUCTION SURVEY WORK | LS | x | 2% | 177237.2929
310 | REMOVAL OF STRUCTURES AND OBSTRUCTIONS | LS | x | 3% | 265855.9394
310 | REMOVAL OF CURBS | FOOT | 225 | 13 | 2925
310 | REMOVAL OF GUARDRAIL | FOOT | 550 | 8 | 4400
310 | REMOVAL OF PIPES | FOOT | 656 | 75 | 49200
310 | REMOVAL OF SURFACINGS | SQYD | 12000 | 65 | 780000
310 | REMOVAL OF WALKS AND DRIVEWAYS | SQYD | 3322.5556 | 114 | 378771.3333
320 | CLEARING AND GRUBBING | ACRE | 2.3438 | 30000 | 70314.7383
330 | GENERAL EXCAVATION | CUYD | 12048.5679 | 76 | 915691.1605
330 | EMBANKMENT IN PLACE | CUYD | 0 | 67 | 0
331 | 12 INCH SUBGRADE STABILIZATION | SQYD | 5399.7333 | 40 | 215989.3333
331 | 24 INCH SUBGRADE STABILIZATION | SQYD | 0 | 63 | 0
340 | WATERING | MGAL | 0 | 25 | 0
350 | SUBGRADE GEOTEXTILE | SQYD | 13499.3333 | 4 | 53997.3333
390 | LOOSE RIPRAP, CLASS 50 | CUYD | 0 | 190 | 0
390 | LOOSE RIPRAP, CLASS 100 | CUYD | 0 | 135 | 0
DRAINAGE AND SEWERS
445 | 18 INCH CULVERT PIPE, 5 FT DEPTH | FOOT | 0 | 240 | 0
445 | 24 INCH CULV PIPE, 5 FT DEPTH | FOOT | 0 | 423 | 0
445 | 36 INCH CULV PIPE, 5 FT DEPTH | FOOT | 0 | 662 | 0
445 | 48 INCH CULV PIPE, 5 FT DEPTH | FOOT | 0 | 0 | 0
| 4 INCH STORM SEWER LATERAL WITH AREA DRAIN | EACH | 30 | 4000 | 120000
445 | 12 INCH STORM SEWER PIPE, 5 FT DEPTH | FOOT | 1951 | 180 | 351180
445 | 15 INCH STORM SEW PIPE, 5 FT | FOOT | 684 | 127 | 86868
445 | 18 INCH STORM SEWER PIPE, 5 FT DEPTH | FOOT | 0 | 266 | 0
445 | 24 INCH STORM SEWER PIPE, 10 FT DEPTH | FOOT | 0 | 0 | 0
445 | 36 INCH STORM SEWER PIPE, 10 FT DEPTH | FOOT | 0 | 0 | 0
445 | 48 INCH STORM SEWER PIPE, 10 FT DEPTH | FOOT | 0 | 0 | 0
470 | CONCRETE STORM SEWER MANHOLES | EACH | 18 | 12360 | 222480
| CONCRETE MANHOLES, OUTLET CONTROL | EACH | 2 | 16000 | 32000
470 | CONCRETE INLETS, TYPE D | EACH | 22 | 4000 | 88000
| DETENTION PONDS | LS | 2 | 100000 | 200000
| INFILTRATION PLANTER - GRADING, SEEDING, AND SOIL | SF | 9350 | 20 | 187000
480 | DRAINAGE CURBS | FOOT | 660 | 70 | 46200
490 | ADJUSTING BOXES | EACH | 0 | 495 | 0
490 | ADJUSTING INLETS | EACH | 0 | 1550 | 0
490 | MAJOR ADJUSTMENT OF MANHOLES | EACH | 20 | 3000 | 60000
BRIDGES/STRUCTURES
| BRIDGES | LS | 0 |  | 0
| TEMP BRIDGE | LS | 0 |  | 0
| BRIDGE REMOVAL | LS | 0 |  | 0
| RETAINING WALL | LIN FT | 0 | 492 | 0
BASES
620 | COLD PLANE PAVEMENT REMOVAL, 0 - 2 INCH DEEP | SQYD | 0 | 5 | 0
620 | COLD PLANE PAVEMENT REMOVAL, 0-3 INCH DEEP | SQYD | 513.7778 | 11.54 | 5928.9956
640 | AGGREGATE BASE | TON | 16867.9951 | 81 | 1366307.6
640 | AGGREGATE SHOULDERS | TON | 17.163 | 60 | 1029.7778
WEARING SURFACES
730 | ASPHALT IN TACK COAT | TON | 0 | 0 | 0
744 | LEVEL 2, 1/2 INCH DENSE MHMAC | TON | 0 | 190 | 0
744 | LEVEL 3, 1/2 INCH DENSE MHMAC | TON | 4731.275 | 300 | 1419382.5
746 | CRACK SEALING | FOOT | 0 | 0 | 0
749 | EXTRA FOR ASPHALT APPROACHES | EACH | 35 | 2000 | 70000
755 | REINFORCED CONCRETE PAVEMENT | SQYD | 0 | 0 | 0
759 | REINFORCED CONCRETE DRIVEWAYS | SQFT | 7736 | 30 | 232080
759 | CONCRETE CURBS | FOOT | 0 | 0 | 0
759 | CURB AND GUTTER CONCRETE CURBS | FOOT | 5713 | 65 | 371345
759 | CONCRETE WALKS | SQFT | 32230 | 20 | 644600
| TACTILE DOMES | SQFT | 400 | 50 | 20000
| EXTRA FOR ADA RAMPS | EACH | 40 | 1700 | 68000
759 | CONCRETE DRIVEWAYS | SQFT | 0 | 15 | 0
PERMANENT TRAFFIC CONTROL AND GUIDANCE DEVICES
810 | GUARDRAIL, TYPE 2A | FOOT | 0 | 0 | 0
810 | GUARDRAIL, TYPE 3 | FOOT | 605 | 80 | 48400
810 | GUARDRAIL, TYPE 4 | FOOT | 0 | 0 | 0
810 | GUARDRAIL ANCHORS, TYPE 1 | EACH | 2 | 2000 | 4000
810 | GUARDRAIL END PIECES, TYPE B | EACH | 0 | 0 | 0
810 | GUARDRAIL TRANSITION | EACH | 2 | 4500 | 9000
810 | GUARDRAIL TERMINALS, NON-FLARED | EACH | 2 | 4500 | 9000
810 | GUARDRAIL TERMINALS, FLARED | EACH | 0 | 0 | 0
812 | ADJUSTING GUARDRAIL | FOOT | 0 | 0 | 0
820 | CONCRETE BARRIER | FOOT | 0 | 0 | 0
820 | CONCRETE BARRIER, TALL | FOOT | 0 | 0 | 0
840 | DELINEATORS, TYPE 2 | EACH | 0 | 0 | 0
840 | MILEPOST MARKER POSTS | EACH | 0 | 0 | 0
867 | PAVEMENT LEGEND, TYPE B: ARROWS | EACH | 20 | 500 | 10000
867 | PAVEMENT LEGEND, TYPE B: "SCHOOL" | EACH | 0 | 0 | 0
867 | PAVEMENT LEGEND, TYPE B: RAILROAD CROSSING MARKINGS | EACH | 0 | 0 | 0
867 | PAVEMENT LEGEND, TYPE B-HS: BICYCLE LANE SYMBOLS | EACH | 10 | 400 | 4000
867 | PAVEMENT BAR, TYPE B | SQFT | 72 | 30 | 2160
867 | PAVEMENT LEGEND, TYPE B: DISABLED PARKING | EACH | 0 | 0 | 0
855 | BI-DIRECTIONAL YELLOW TYPE I MARKERS | EACH | 88 | 9 | 792
855 | MONO-DIRECTIONS WHITE PAVEMENT MARKERS | EACH | 6 | 25 | 150
860 | LONGITUDINAL PAVEMENT MARKINGS - PAINT | FOOT | 0 | 0 | 0
865 | THERMOPLASTIC, EXTRUDED, SURFACE, PROFILED | FOOT | 5135 | 4 | 20540
857 | CONTINUOUS RUMBLE STRIPS | MILE | 0 | 0 | 0
PERMANENT TRAFFIC CONTROL AND ILLUMINATION SYSTEMS
940 | PERMANENT SIGNS | LS | 1 | 25000 | 25000
| INTERPRETIVE PANELS AND DÉCORATIVE HARDSCAPE FEATURES | LS | 0 | 0 | 0
990 | DETECTOR INSTALLATION, _____ | EACH | 0 | 0 | 0
990 | TRAFFIC SIGNAL INSTALLATION, _____ | EACH | 0 | 0 | 0
990 | INTERCONNECT SYSTEM | LS | 0 | 0 | 0
990 | STREET LIGHTS SINGLE - INCLUDING CONECTIONS, WIRING, CONDUIT | EACH | 15 | 18000 | 270000
| STREET LIGHTS MULTIPLE - INCLUDING CONECTIONS, WIRING, CONDUIT | EACH | 0 | 0 | 0
| ILLUMINATION |  | 0 | 0 | 0
| MODIFY RRFB | EACH | 2 | 15000 | 30000
RIGHT-OF-WAY DEVELOPMENT AND CONTROL
1030 | PERMANENT SEEDING, MIX NO. 1 | ACRE | 0.64279 | 15000 | 9641.8733
1050 | _____ CHAIN LINK FENCE | LIN FT | 812 | 110 | 89320
1070 | SINGLE MAILBOX SUPPORTS | EACH | 4 | 700 | 2800
1070 | MULTIPLE MAILBOX SUPPORTS | EACH | 15 | 1250 | 18750
| ENVIRONMENTAL IMPACT COSTS (ROADSIDE DITCH IMPACTS) | LS | 1 | 100000 | 100000
| LANDSCAPING - TREES, GROUNDCOVER, AND IRRIGATION (NON-SWQ) | SF | 14462 | 10 | 144620
UNUSUAL ELEMENTS
1095 | LITTER RECEPTACLES | EACH | 0 | 0 | 0
1095 | BENCHES, TYPE ________ | EACH | 0 | 0 | 0
1040 | TREE GRATES | EACH | 0 | 0 | 0
1095 | BIKE RACKS | EACH | 0 | 0 | 0
759 | METAL HANDRAIL, 2 RAILS | LIN FT | 0 | 0 | 0
CONSTRUCTION SUBTOTAL |  |  |  |  | 11352048.6108
PROJECT PHASES/SUMMARY OF COSTS
ROW
| LAND, IMPROVEMENTS, DAMAGES | LS | 1 | 850003 | 850003 | 32,250 sf takes + 28,000 sf TCE + 20,068 sf slope easements + 2 Full Takes at 2650 TRR and 3088 TRR
| ROW PROCESS (APPR, REV APPR, ACQ, ODOT REV, etc.) | File | 62 | 10000 | 620000 | 45 takes + 17 TCE-only
| ROW SUBTOTAL |  |  |  | 1470003
UTILITY RELOCATION
INSERT APPROPRIATE LINE ITEMS/COSTS FOR ANY REIMBURSABLE UTILITIES
| UTILITY RELOCATION SUBTOTAL | LS | 1% | of CON cost | 113520.4861
PRELIMINARY ENGINEERING
| PE - ODOT OVERSIGHT | LS | 1 | 50000 | 50000
| *PE - ENVIRONMENTAL | LS | 3% | of CON cost | 340561.4583
| PE - SURVEYING | LS | 5% | of CON cost | 567602.4305
| PE - GEO-TECH | LS | 3% | of CON cost | 340561.4583
| **PE - DESIGN & PROJECT MANAGEMENT | LS | 20% | of CON cost | 2270409.7222
| PRELIMINARY ENGINEERING SUBTOTAL |  |  |  | 3569135.0693
CONSTRUCTION
| TOTAL BID ITEM COST (from estimate above) |  |  |  | 11352048.6108
| CE- ODOT OVERSIGHT | LS | 1 | 25000 | 25000
| ***CONSTRUCTION ENGINEERING ADMIN & INSPECTION | LS | 17% | of CON cost | 1929848.2638
| CONSTRUCTION CONTINGENCY | LS | 30% | of CON cost | 3405614.5832
| CONSTRUCTION SUBTOTAL |  |  |  | 16712511.4578
TOTAL PROJECT COST (2025 $) |  |  |  |  | 21865170.0132
EXPECTED YEAR OF CONSTRUCTION |  | 2029
ESTIMATED INFLATION |  | 3.3%
TOTAL PROJECT COST (2029 $) |  |  |  |  | 24897408.4807
* | Environmental costs should account for the typical clearances needed for each environmental area (historic-archaeological & built, hazmat, biology, wetland, noise, etc.), any necessary permits and land use requirements. Contact ODOT LAL for assistance, if needed.
** | Typical percentages for federally funded LPA projects range from 20% to 30%. Projects with lower construction costs (under $1M) typically have higher design percentages.
*** | Typical percentages for federally funded LPA projects range from 17% to 25%. Projects with lower construction costs (under $1M) typically have higher CE percentages.
Note on E50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MAJOR ADJUSTMENT AVG PRICE WAS $3876, MINOR ADJUSTMENT AVG PRICE WAS $1867. USED $3K TO COVER SOME OF EACH SINCE THE AMOUNT OF ADJUSTMENT NEEDED IS UNKNOWN AT THIS TIME.

## Sheet1
ROW Cost per SF
Tax Lot | Size (ac) | Size (sf) | County Assessor Value (RMV $) | $/sf
372w13bd 700 | 0.48 | 20908.8 | 159000 | 7.6045
372w13ac 700 | 0.57 | 24829.2 | 240000 | 9.666
372w13ab 1700 | 0.73 | 31798.8 | 214000 | 6.7298
372w13ba 600 | 0.46 | 20037.6 | 159000 | 7.9351
372w13bd 900 | 0.3 | 13068 | 131000 | 10.0245
372w13bd 1200 | 0.18 | 7840.8 | 111000 | 14.1567
372w13ba 201 | 0.42 | 18295.2 | 158000 | 8.6361
372w13ba 400 | 0.48 | 20908.8 | 161000 | 7.7001
372w13ba 300 | 0.68 | 29620.8 | 214000 | 7.2247
372w12d 9000 | 1.21 | 52707.6 | 278600 | 5.2858
372w13ba 6500 | 0.46 | 20037.6 | 159000 | 7.9351
372w12d 8900 | 1 | 43560 | 285420 | 6.5523
372w12d 8700 | 1.59 | 69260.4 | 273000 | 3.9416
372w13ba 2400 | 0.23 | 10018.8 | 128000 | 12.776
372w12cd 1200 | 0.46 | 20037.6 | 159000 | 7.9351
372w12cd 900 | 0.22 | 9583.2 | 129000 | 13.4611
372w12d 8601 | 0.52 | 22651.2 | 134240 | 5.9264
372w12d 8600 | 1.63 | 71002.8 | 274000 | 3.859
372w12cd 800 | 0.21 | 9147.6 | 131000 | 14.3207
Average | 0.62263 |  |  | 8.509