## Cost Estimate Scoping Sheet
RVMPO/MRMPO SCOPING ESTIMATE
(updated May 2025)
PROJECT NAME |  |  |  | COUNTY
KIND OF WORK |  | LENGTH | DATE | ESTIMATE PREPARER
Section # | ITEM TITLE | UNIT | QTY | UNIT | EXTENDED
|  |  |  | COST | COST
TEMPORARY FEATURES AND APPURTENANCES
210 | MOBILIZATION | LS | x | 10% | 55053.4084
221 | TEMPORARY PROTECTION AND DIRECTION OF TRAFFIC | LS | x | 10% | 55053.4084
280 | EROSION CONTROL | LS | x | 2% | 10290.3567
ROADWORK
305 | CONSTRUCTION SURVEY WORK | LS | x | 2% | 10472.4003
310 | REMOVAL OF STRUCTURES AND OBSTRUCTIONS | LS | x | 3% | 14680.935
310 | REMOVAL OF CURBS | FOOT |  | 5 | 0
310 | REMOVAL OF GUARDRAIL | FOOT |  | 5 | 0
310 | REMOVAL OF PIPES | FOOT |  | 30 | 0
310 | REMOVAL OF SURFACINGS | SQYD |  | 25 | 0
310 | REMOVAL OF WALKS AND DRIVEWAYS | SQYD |  | 30 | 0
320 | CLEARING AND GRUBBING | ACRE | 4 | 4500 | 19260
330 | GENERAL EXCAVATION | CUYD | 2500 | 30 | 80250
330 | EMBANKMENT IN PLACE | CUYD |  | 30 | 0
331 | 12 INCH SUBGRADE STABILIZATION | SQYD |  | 20 | 0
331 | 24 INCH SUBGRADE STABILIZATION | SQYD |  | 40 | 0
340 | WATERING | MGAL |  | 25 | 0
350 | SUBGRADE GEOTEXTILE | SQYD |  | 1 | 0
390 | LOOSE RIPRAP, CLASS 50 | CUYD |  | 75 | 0
390 | LOOSE RIPRAP, CLASS 100 | CUYD |  | 100 | 0
DRAINAGE AND SEWERS
445 | 18 INCH CULVERT PIPE, 5 FT DEPTH | FOOT |  | 70 | 0
445 | 24 INCH CULV PIPE, 5 FT DEPTH | FOOT |  | 100 | 0
445 | 36 INCH CULV PIPE, 5 FT DEPTH | FOOT |  | 150 | 0
445 | 48 INCH CULV PIPE, 5 FT DEPTH | FOOT |  | 250 | 0
445 | 12 INCH STORM SEWER PIPE, 5 FT DEPTH | FOOT |  | 60 | 0
445 | 15 INCH STORM SEW PIPE, 5 FT | FOOT |  | 75 | 0
445 | 18 INCH STORM SEWER PIPE, 5 FT DEPTH | FOOT |  | 90 | 0
445 | 24 INCH STORM SEWER PIPE, 10 FT DEPTH | FOOT |  | 125 | 0
445 | 36 INCH STORM SEWER PIPE, 10 FT DEPTH | FOOT |  | 175 | 0
445 | 48 INCH STORM SEWER PIPE, 10 FT DEPTH | FOOT |  | 275 | 0
470 | CONCRETE STORM SEWER MANHOLES | EACH |  | 5000 | 0
470 | CONCRETE INLETS, TYPE CG-2 | EACH |  | 2400 | 0
480 | DRAINAGE CURBS | FOOT |  | 10 | 0
490 | ADJUSTING BOXES | EACH |  | 500 | 0
490 | ADJUSTING INLETS | EACH |  | 1000 | 0
490 | MAJOR ADJUSTMENT OF MANHOLES | EACH |  | 2500 | 0
BRIDGES/STRUCTURES
| BRIDGES | LS |  |  | 0
| TEMP BRIDGE | LS |  |  | 0
| BRIDGE REMOVAL | LS |  |  | 0
| RETAINING WALL | LIN FT | 500 | 492 | 263220
BASES
620 | COLD PLANE PAVEMENT REMOVAL, 0 - 2 INCH DEEP | SQYD |  | 5 | 0
620 | COLD PLANE PAVEMENT REMOVAL, 2 INCH DEEP | SQYD |  | 2 | 0
640 | AGGREGATE BASE | TON | 350 | 35 | 13107.5
640 | AGGREGATE SHOULDERS | TON | 250 | 20 | 5350
WEARING SURFACES
730 | ASPHALT IN TACK COAT | TON |  | 600 | 0
744 | LEVEL 2, 1/2 INCH DENSE MHMAC | TON | 250 | 100 | 26750
744 | LEVEL 3, 1/2 INCH DENSE MHMAC | TON |  | 100 | 0
746 | CRACK SEALING | FOOT |  | 5 | 0
749 | EXTRA FOR ASPHALT APPROACHES | EACH |  | 575 | 0
755 | REINFORCED CONCRETE PAVEMENT | SQYD |  | 125 | 0
759 | REINFORCED CONCRETE DRIVEWAYS | SQFT |  | 15 | 0
759 | CONCRETE CURBS | FOOT |  | 25 | 0
759 | CURB AND GUTTER CONCRETE CURBS | FOOT |  | 40 | 0
759 | CONCRETE WALKS | SQFT |  | 15 | 0
759 | CONCRETE DRIVEWAYS | SQFT |  | 15 | 0
PERMANENT TRAFFIC CONTROL AND GUIDANCE DEVICES
810 | GUARDRAIL, TYPE 2A | FOOT |  | 35 | 0
810 | GUARDRAIL, TYPE 3 | FOOT | 800 | 60 | 51360
810 | GUARDRAIL, TYPE 4 | FOOT |  | 85 | 0
810 | GUARDRAIL ANCHORS, TYPE 1 | EACH |  | 780 | 0
810 | GUARDRAIL END PIECES, TYPE B | EACH | 2 | 100 | 214
810 | GUARDRAIL TRANSITION | EACH |  | 3000 | 0
810 | GUARDRAIL TERMINALS, NON-FLARED | EACH |  | 3500 | 0
810 | GUARDRAIL TERMINALS, FLARED | EACH |  | 3500 | 0
812 | ADJUSTING GUARDRAIL | FOOT |  | 3.5 | 0
820 | CONCRETE BARRIER | FOOT |  | 61 | 0
820 | CONCRETE BARRIER, TALL | FOOT |  | 85 | 0
840 | DELINEATORS, TYPE 2 | EACH |  | 38 | 0
840 | MILEPOST MARKER POSTS | EACH |  | 100 | 0
867 | PAVEMENT LEGEND, TYPE B: ARROWS | EACH |  | 270 | 0
867 | PAVEMENT LEGEND, TYPE B: "SCHOOL" | EACH |  | 495 | 0
867 | PAVEMENT LEGEND, TYPE B: RAILROAD CROSSING MARKINGS | EACH |  | 975 | 0
867 | PAVEMENT LEGEND, TYPE B-HS: BICYCLE LANE SYMBOLS | EACH |  | 280 | 0
867 | PAVEMENT BAR, TYPE B | SQFT |  | 8.5 | 0
867 | PAVEMENT LEGEND, TYPE B: DISABLED PARKING | EACH |  | 287 | 0
855 | BI-DIRECTIONAL YELLOW TYPE I MARKERS | EACH |  | 4.75 | 0
855 | BI-DIRECTIONAL YELLOW TYPE I MARKERS, RECESSED | EACH |  | 6 | 0
860 | LONGITUDINAL PAVEMENT MARKINGS - PAINT | FOOT |  | 0.15 | 0
865 | THERMOPLASTIC, EXTRUDED, SURFACE, PROFILED | FOOT |  | 1 | 0
857 | CONTINUOUS RUMBLE STRIPS | MILE |  | 1500 | 0
PERMANENT TRAFFIC CONTROL AND ILLUMINATION SYSTEMS
940 | PERMANENT SIGNS | LS |  |  | 0
| INTERPRETIVE PANELS AND DÉCORATIVE HARDSCAPE FEATURES | LS |  |  | 0
990 | DETECTOR INSTALLATION, _____ | EACH |  | 2600 | 0
990 | TRAFFIC SIGNAL INSTALLATION, _____ | EACH |  | 178000 | 0
990 | INTERCONNECT SYSTEM | LS |  | 30000 | 0
990 | STREET LIGHTS SINGLE - INCLUDING CONECTIONS, WIRING, CONDUIT | EACH |  |  | 0
| STREET LIGHTS MULTIPLE - INCLUDING CONECTIONS, WIRING, CONDUIT | EACH |  |  | 0
| ILLUMINATION |  |  |  | 0
RIGHT-OF-WAY DEVELOPMENT AND CONTROL
1030 | PERMANENT SEEDING, MIX NO. 1 | ACRE | 3 | 4500 | 14445
1050 | _____ CHAIN LINK FENCE | LIN FT |  | 18 | 0
1070 | SINGLE MAILBOX SUPPORTS | EACH |  | 150 | 0
1070 | MULTIPLE MAILBOX SUPPORTS | EACH |  | 350 | 0
| ENVIRONMENTAL MITIGATION SITES | LS |  |  | 0
| LANDSCAPING | LS |  |  | 0
UNUSUAL ELEMENTS
1095 | LITTER RECEPTACLES | EACH |  | 1600 | 0
1095 | BENCHES, TYPE ________ | EACH |  | 1700 | 0
1040 | TREE GRATES | EACH |  | 1300 | 0
1095 | BIKE RACKS | EACH |  | 600 | 0
759 | METAL HANDRAIL, 2 RAILS | LIN FT | 200 | 72 | 15408
0
CONSTRUCTION SUBTOTAL |  |  |  |  | 634915.0088
PROJECT PHASES/SUMMARY OF COSTS
ROW
| LAND, IMPROVEMENTS, DAMAGES | LS
| ROW PROCESS (APPR, REV APPR, ACQ, ODOT REV, etc.) | File |  | 15000 | 0
| ROW SUBTOTAL |  |  |  | 0
UTILITY RELOCATION
INSERT APPROPRIATE LINE ITEMS/COSTS FOR ANY REIMBURSABLE UTILITIES
| UTILITY RELOCATION SUBTOTAL |  |  |  | 0
PRELIMINARY ENGINEERING
| PE - ODOT OVERSIGHT | LS | 1 | 107150 | 107150
| *PE - ENVIRONMENTAL | LS | 1 | 85000 | 85000
| PE - SURVEYING | LS | 1 | 56000 | 56000
| PE - GEO-TECH | LS | 1 | 150000 | 150000
| **PE - DESIGN & PROJECT MANAGEMENT | LS | 20% | of CON cost | 126983.0018
| PRELIMINARY ENGINEERING SUBTOTAL |  |  |  | 525133.0018
CONSTRUCTION
| TOTAL BID ITEM COST (from estimate above) |  |  |  | 634915.0088
| CE- ODOT OVERSIGHT | LS | 1 | 25000 | 25000
| ***CONSTRUCTION ENGINEERING ADMIN & INSPECTION | LS | 15% | of CON cost | 95237.2513
| CONSTRUCTION CONTINGENCY | LS | 30% | of CON cost | 190474.5026
| CONSTRUCTION SUBTOTAL |  |  |  | 945626.7627
TOTAL PROJECT COST |  |  |  |  | 1470759.7645
* | Environmental costs should account for the typical clearances needed for each environmental area (historic-archaeological & built, hazmat, biology, wetland, noise, etc.), any necessary permits and land use requirements. Contact ODOT LAL for assistance, if needed.
** | Typical percentages for federally funded LPA projects range from 20% to 30%. Projects with lower construction costs (under $1M) typically have higher design percentages.
*** | Typical percentages for federally funded LPA projects range from 17% to 25%. Projects with lower construction costs (under $1M) typically have higher CE percentages.

## ROW
RIGHT OF WAY SCOPING WORKSHEET
Project Name | [5 empty] | Project Number
|  |  | Begin | End | Begin | End
Street / Road / Route |  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
Type of Project |  |  | County |  | City |  | MPO
Work Type
Rural/Urban/Mixed
Terrain
R/W Cost Estimate
Contact for Project: | [6 empty] | R/W Subtotal | 0
Prepared By: |  |  |  | Date: |  |  | Access Mgmt Subtotal (from AM Sheet) | 0
[7 empty] | Total R/W Estimate | 0
|  | Yes | No | N/A | Comment/Clarification
RIGHT OF WAY REQUIRED
Fee Parcels
Permanent Easement(s)
Temporary Easement(s)
Rights of Entry
Archy, Geo, Enviro
Other
Access Remedies
Roadway
Slopes
Drainage
Utilities
Sign(s)
Signals
Aerial
Sidewalk
Temporary Easements |  | Yes | No | N/A | Comment/Clarification
Construction
Demolition
BLM
Forest Service
Corp of Engineers
DSL Lands
Airport
Section 4F/6F Properties
Parks
Schools
Wildlife Refuges
Historic Buildings
Recreational Areas
Other
Right of Way Acquisition Impacts to Consider
|  | Yes | No | N/A | Comment/Clarification
Gas Stations
Repair Shops
Industrial Sites
Landfills
Fuel Tanks
Privately Owned Wells
Water Rights
Irrigation Ditches
Septic Systems
On-Premise Signs
Outdoor Advertising Signs
Cell Tower Sites
Public Utilities
Special Relocate Considerations
Miscellaneous Features with Significant Impacts
Are there Land Services considerations such as
|  | Yes | No | N/A | Comment/Clarification
Exisitng Frontage Roads
Proposed Frontage Roads
Access Roads
Cattle or Equipment Passes
Major Irrigation Installations
Other (specify)
Current Access Control
Access Control Proposed
Permitted Access
Grandfathered Access
Reservations of Access
Indentures of Access
Has the RAME been contacted regarding any access modifications?
Known property owners concerns:
Other right of way comments, concerns or considerations:
Number and Type of Right of Way Acquisitions:
Total Files: |  |  |  |  | Comment/Clarification
Simple Acquisitions:
Complex Acquisitions:
Residential Relocations:
Business Acquisitions:
Hardship Relocations:
Railroad Acquisitions:
Government Acquisitions
Narrative | (To start a new paragraph within a cell, press Alt/Enter)
Assumptions

## Utilities
UTILITIES SCOPING WORKSHEET
Project Name |  |  |  |  | Project Number
|  | Begin | End | Begin | End
Street / Road / Route |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
Type of Project |  | County |  | City |  | MPO
Work Type
Rural/Urban/Mixed
Terrain
Contact for Project:
Prepared By: |  |  | Date:
Utilities |  | Yes | No | N/A | Comment/Clarification
Utility Impacts
Reimbursable Utilities |  |  |  |  | Supporting Franchise Agreements availble?
If Yes, cost estimate: |  | 0
List of Expected Utilities
Utility Name |  |  | Comment/Clarification
Narrative | (To start a new paragraph within a cell, press Alt/Enter)
Assumptions

## Enviromental
ENVIRONMENTAL SCOPING WORKSHEET
Project Name |  |  |  |  | Project Number
|  | Begin | End | Begin | End
Street / Road / Route |  | 0 | 0 | 0
|  | 0 | 0 | 0
|  | 0 | 0 | 0
|  | 0 | 0 | 0
Type of Project |  | County |  | City |  | MPO
Work Type
Rural/Urban/Mixed
Terrain
Contact for Project:
Prepared By: |  |  | Date:
Environmental Classification:
Applicable NEPA Documents |  |  | Yes | No | N/A | Provide explanation
Is the project associated with any completed NEPA documents (EA or EIS) or Alternative Selection process? (Explain)
Does the project completely or partially fulfill the related FONSI or ROD? (Explain)
Does the NEPA document need to be updated based on time or changed conditions before design can proceed?
Is the project a Class 2 action that falls within the API of a NEPA document and is not subject to the FONSI or ROD? (Explain)
Air Quality |  |  | Yes | No | N/A | Comment/Clarification
Non-Attainment or Maintenance Area
CO
Ozone
PM10
Other Considerations |  |  | Yes | No | N/A | Comment/Clarification
Additional Lanes
Signalization
Channelization
Alignment Changes
|  |  | Yes | No | N/A | Comment/Clarification
Archaeology
Potentially sensitive areas
New ground disturbance
BLM & USFS known sites
Subsurface proping needed
Biology
US Quad Name: |  |  | T |  | R |  | Section
|  |  | Yes | No | N/A | Comment/Clarification
ODFW Contact Made
T&E Species present
Streams impacted
Essential Salmonid Habitat
Medium or High Priority fish passage culverts
In-Water Work Period (specify in Comments)
Energy: |  |  | Yes | No | N/A | Comment/Clarification
Speed zone changes
Traffic pattern changes
Traffic volume changes
Geology: |  |  | Yes | No | N/A | Comment/Clarification
Drilling required
Hazardous Materials |  |  | Yes | No | NA | Comment/Clarification
Documented hazmat sites
Hazmat |  |  | Yes | No | N/A | Comment/Clarification
Gas Stations, Industrial Sites
Repair, Land Fill Facilities
Historical Resources |  |  | Yes | No | N/A | Comment/Clarification
Historic Resources*
Listed Goal 5 Resources
*National Register of Historic Places, State of Historic Preservation, Structures of 50 years in age?
Land Use |  |  | Yes | No | N/A | Comment/Clarification
In UGB
Forest or EFU Lands
Noise |  |  | Yes | No | N/A | Comment/Clarification
New or changed alignment
Additional lanes
|  |  | Yes | No | N/A | Comment/Clarification
Section 4F
Section 6F
Socioeconomics |  |  | Yes | No | N/A
Building displacements that are key to economy/neighborhood.
Number of Displacements: |  | 0
General use of adjacent land: |  | Number
Residential
Commercial
Farm/Range
Public
Other |  |  | List:
|  |  | Yes | No | N/A | Comment/Clarification
Visual Resources Impacts
Major Cuts /Fills
Bridges or Retaining Walls
Scenic Waterways
Wild and Scenic Waterways
Adjacent to Federal Lands
Federal Enhancement
Scenic Byway Program
Oregon Historic Highway (ORS 377.100)
Oregon Scenic Area (ORS 377.505)
Scenic-Forest Practices Act (ORS 527.755)
Waterways & Water Quality |  |  | Yes | No | N/A | Comment/Clarification
Within 100-year Floodplain
Within FEMA Regulated Floodway
Water quality limited streams impacted
Active wells impacted
Navigable waterways impacted
New impervious surface area > 1000 sq yd
Impacts irrigation district
T&E species in receiving water
Existing storm drainage system
Stormwater Management Plan required
Comment/Clarification
Wetlands |  |  | Yes | No | N/A
Wetlands present
Wetland mitigation needed (estimate cost in Comments)
Wetland-related Permits: | [5 empty] | Comment/Clarification
US Army Corp of Engineers Section 10 / Section 404
DSL Removal/Fill
DEQ Indirect Air:
PUC Railroad:
NPDES (Pollutant Discharge Elimination):
Other
Coast Guard |  |  | Yes | No | N/A
Coast Guard coordination required
Coast Guard permit required
Clearances Required: |  |  | Yes | No | N/A | Comment/Clarification (Note required documentation)
ESA (BA, BO)
SHPO (Historical)
SHPO (Archaeological)
Fish passage plan
Noise
DEQ Noise
Air Quality
Hazmat | [5 empty] | Level 1 Hazmat Evaluation
Narrative | (To start a new paragraph with a cell, press Alt/Enter)
Assumptions

## Survey
SURVEYING SCOPING WORKSHEET
Project Name | [5 empty] | Project Number
|  |  | Begin | End | Begin | End
Street / Road / Route |  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
Type of Project |  |  | County |  | City |  | MPO
Work Type |  |  |  | 0 |  | 0
Rural/Urban/Mixed |  |  |  | 0 |  | 0
Terrain |  |  |  | 0
Contact for Project:
Prepared By: |  |  |  | Date:
Reviewed By: |  |  |  | Date:
|  | Yes | No | N/A
Is survey required on this project?
Aerial Photography required?
Usable existing field survey?
Beginning of Project Latitude:
Beginning of Project Longitude:
Existing ODOT R/W Drg No.(s):
Existing Filing Maps:
Narrative | (To start a new paragraph within a cell, press Alt/Enter)
Assumptions

## Geology-Geotech
GEOLOGY/GEOTECH SCOPING WORKSHEET
Project Name |  |  |  |  | Project Number
|  | Begin | End | Begin | End
Street / Road / Route |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
Type of Project |  | County |  | City |  | MPO
Work Type
Rural/Urban/Mixed
Terrain
Contact for Project:
Prepared By: |  |  | Date:
Reviewed By: |  |  | Date:
Issues to be addressed |  |  | Yes | No | N/A | Comment/Clarification
Disposal Site Required
Site Available (specify location in comment section)
Material Source Required
Site Available (specify location in comment section)
Structure Added or Modified
Bridge
Retaining Wall
Sound Wall
Culvert
Sign/Signal
VMS
Other
|  |  | Yes | No | NA | Comment/Clarification
Instability (Landslide or Rockfall)
Roadway Failure (Sinkholes etc.)
Groundwater Problems
Drainage Concerns
Subsurface Investigation Required
Narrative | (To start a new paragraph within a cell, press Alt/Enter)
Assumptions

## Structure Narrative
BRIDGE SCOPING NARRATIVE
Project Name |  | Scoping No.
Bridge Design Category
Scoped by |  | Scoping Date
Reviewed by |  | Review Date
Bridge No. | Structure Name | Highway | MP
Narrative
Assumptions
Risks
Sketches
Photos

## Structure Estimate
STRUCTURE COST ESTIMATE SUMMARY
PROJECT
SCOPING No.
[5 empty] | ESTIMATED ITEMS |  |  | BID ITEMS
ITEM No. | BRIDGE No. | SPEC GROUP | SPEC | CLASS OF WORK | MEASURE. | QTY | UNIT COST | SPEC UNIT | QTY | UNIT COST | TOTAL | NOTES
Note on H7: This is the unit for an estimate (e.g. LS is not helpful in determining a cost, so use a distance, area, or volume instead).
Note on J7: Unit Cost can be overwritten: Red = Cost is less than default Orange = Cost is more than default
Note on K7: This is the required unit from the spec